## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 36
PROJECT NAME | Personalised Ads - Box Ads
PROJECT MENTOR (sponsor) | Praveen Reddy (Client)
TEAM MEMBERS | Sai Praneeth Bommana
Sai Sudhan Kunapareddy
Chaganti Venkata Karthikeya
Kriti Madumadukala
Vivek Hruday Kavuri

## Status
PROJECT NUMBER | 36
PROJECT NAME | Personalised Ads - Box Ads
PROJECT MENTOR (sponsor) | Praveen Reddy (Client)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Rudransh(T.A) | 1.5 | 2.5 | Done |  | -1 | 40
GIT Repository setup | Preparation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Questions for requirements elicitation | Documentation | Praneeth, Vivek | 2 | 1.5 | Done | Make sure scoping questions are included
Client meeting | Coordination | Karthieya, Sudhan | 1 | 1 | Done |  | 0 | 0
Research existing technology | Preparation | Praneeth | 1.5 | 2 | Done |  | -0.5 | 25
Project synopsis writeup | Documentation | Praneeth, Vivek | 1.5 | 1 | Done |  | 0.5 | 50
Identify role owners | Identify role owners | Kriti | 1 | 0.5 | Planned |  | 0.5 | 100
Team Meeting | Coordination | Sudhan, Karthikeya | 2 | 1.5 | Done |  | 0.5 | 33.3333
Status tracker | Documentation | Sudhan | 2 | 1 | Done |  | 1 | 100
Week 2 (January 22 - January 28)
Intro to MERN | Requirements | All | 5 | 5 | Ongoing | Getting familiarised with the technologies required. | 0 | 0
Develop questions for requirements elicitation | Documentation | Praneeth, Vivek | 2 | 1 | Done | Make sure scoping questions are included | 1 | 100
Client meeting | Coordination | All | 1 | 0 | Done |  | 1
Team Meeting | Coordination | Kriti | 1 | 1.5 | Done |  | -0.5 | 33.3333
Project Planning | Documentation | All | 2 | 0.5 | Ongoing | Estimation, scheduling of various tasks | 1.5 | 300
Status tracker | Documentation |  | 2 | 0 | Planned |  | 2
Week 3 (January 29 - February 4)
Intro to MERN | Requirements | All | 5 | 5 | Planned | Learning the technological skills required. | 0 | 0
Team Meeting | Coordination |  | 3 |  | Planned
Develop questions for requirements elicitation | Documentation |  | 1.5 |  | Planned | Make sure scoping questions are included
Designing the modules required based on requirements | Design |  | 2.5 |  | Planned | Make sure all the specifications are met.
Client meeting | Coordination |  | 1 |  | Planned
Status tracker | Documentation |  | 2 |  | Planned
Week 4
Week 5
Week 6
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically