## Instructions
Using the Status tracker
At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
If 5 team members each spent an hour, that counts as 5 hours
Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)
For new activities, identify the type of activity - documentation, coordination, estimation etc.
At the end of each week, plan ahead for the following week
Identify people responsible for each activity
Estimate the hours needed for the activity
PROJECT NUMBER | 36
PROJECT NAME | Personalised Ads - Box Ads
PROJECT MENTOR (sponsor) | Praveen Reddy (Client)
TEAM MEMBERS | Sai Praneeth Bommana
Sai Sudhan Kunapareddy
Chaganti Venkata Karthikeya
Kriti Madumadukala
Vivek Hruday Kavuri

## Status
PROJECT NUMBER | 36
PROJECT NAME | Personalised Ads - Box Ads
PROJECT MENTOR (sponsor) | Praveen Reddy (Client)
Activity Name | Type | Responsible | Estimated Team Hours | Actual Hours | Status | Comments | Estimation error | Estimation error %
See Instructions sheet for usage
Week 1 (January 16- January 21)
Fix meeting with client | Coordination | Rudransh(T.A) | 1.5 | 2.5 | Done |  | -1 | 40
GIT Repository setup | Preparation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Questions for requirements elicitation | Documentation | Praneeth, Vivek | 2 | 1.5 | Done | Make sure scoping questions are included
Client meeting | Coordination | Karthieya, Sudhan | 1 | 1 | Done |  | 0 | 0
Technology | Preparation | Praneeth | 1.5 | 2 | Done |  | -0.5 | 25
Project synopsis writeup | Documentation | Praneeth, Vivek | 1.5 | 1 | Done |  | 0.5 | 50
Identify role owners | Identify role owners | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Team Meeting | Coordination | Sudhan, Karthikeya | 2 | 1.5 | Done |  | 0.5 | 33.3333
Status tracker | Documentation | Sudhan | 1.5 | 1 | Done |  | 0.5 | 50
Week 2 (January 22 - January 28)
Intro to MERN | Requirements | All | 5 | 5 | Done | Getting familiarised with the technologies required. | 0 | 0
Develop questions for requirements elicitation | Documentation | Praneeth, Vivek | 2 | 1 | Done | Make sure scoping questions are included | 1 | 100
Client meeting | Coordination | All | 1 | 1 | Done |  | 0 | 0
Team Meeting | Coordination | Kriti | 1 | 1.5 | Done |  | -0.5 | 33.3333
Project Planning | Documentation | All | 2 | 2 | Done | Estimation, scheduling of various tasks | 0 | 0
Client meeting - MOM | Documentation | Karthikeya | 1.5 | 1 | Done
Status tracker | Documentation | Kriti | 1.5 | 1 | Done |  | 0.5 | 50
Week 3 (January 29 - February 4)
Intro to MERN | Requirements | All | 5 | 3 | Done | Learning the technological skills required. | 2 | 66.6667
Team Meeting | Coordination | Vivek | 1.5 | 1 | Done |  | 0.5 | 50
Develop questions for requirements elicitation | Documentation | Sudhan | 1.5 | 1 | Done | Make sure scoping questions are included
Designing the modules required based on requirements | Design | All | 2.5 | 2 | Done | Make sure all the specifications are met.
Client meeting | Coordination | Karthikeya | 1.5 | 1 | Done
Client meeting - MOM | Documentation | Kriti | 1.5 | 1 | Done
Status tracker | Documentation | Praneeth | 1 | 1 | Done |  | 0 | 0
Week 4
Designing the modules required based on requirements | Design | Karthieya, Sudhan | 4 | 3 | Done |  | 1 | 33.3333
Develop questions for requirements elicitation | Documentation | Kriti | 1.5 | 0.5 | Done |  | 1 | 200
High level Design 1 | Design | Vivek | 2 | 1 | Done
Admin Dashboard Design 1 | Design | Praneeth | 4 | 3.5 | Done
Client meeting | Coordination | Praneeth, Vivek | 0.5 | 0.4 | Done
Client meeting - MOM | Documentation | Vivek | 1 | 0.5 | Done
Team Meeting | Coordination | Karthieya, Sudhan | 1 | 0.75 | Done
Status tracker | Documentation | Kriti | 1 | 0.5 | Done
Week 5
Adveriser Dashboard Design | Design | Vivek, Karthikeya | 2 | 1.5 | Done |  | 0.5 | 33.3333
Logistics Partner Dashboard design | Design | Vivek, Karthikeya | 2 | 1.5 | Done
Designing the project plan for frontend and backend | Design | Praneeth | 1.5 | 1 | Done
Develop questions for requirements elicitation | Documentation | Sudhan | 1.5 | 1 | Done
Start Coding | Development | All | 3 | 3.5 | Done
Client meeting | Coordination | Praneeth | 1 | 0.5 | Done |  | 0.5 | 100
Client meeting - MOM | Documentation | Kriti | 1.5 | 1 | Done |  | 0.5 | 50
SRS | Requirements | Karthikeya | 2 | 1.5 | Done
Use case Description | Documentation | Sudhan, Praneeth | 3 | 2 | Done
Uml use case diagram | Design | Vivek, Kriti | 2 | 1.5 | Done
SRS document | Documentation | All | 6 | 5 | Done
Team Meeting | Coordination | Sudhan | 1.5 | 1 | Done
Status tracker | Documentation | Kriti | 1 | 0.5 | Done
Week 6
Client meeting | Coordination | Praneeth, Vivek | 1 |  | Done | Done on 3rd March 2024
Client meeting - MOM | Documentation | Kriti | 1.5 | 0.5 | Done | After client meet | 1 | 200
User authentication - UI + backend | Development | Praneeth | 5 | 4 | Done |  | 1 | 25
Creating Schemas for questions and Adding questions into the database | Development | Sudhan, Karthikeya | 5 | 4 | Done |  | 1 | 25
Advertiser sending ads to the database - Backend | Development | Vivek, Kriti | 5 | 4 | Done |  | 1 | 25
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 1 | Done | On 24th Feb 2024 | 0 | 0
Test plan | Documentation | All | 3 | 1.5 | Done |  | 1.5 | 100
Status tracker | Documentation | Kriti | 1 | 0.5 | Done
Week 7
Adding questions to the Form page | Development | Sudhan, Karthikeya | 4 | 3.5 | Done |  | 0.5 | 14.2857
Advertiser sending ads for approval of the ads and User interface | Development | Vivek, Kriti | 4 | 3.5 | Done |  | 0.5 | 14.2857
Backend and userinterface for user authentication/ login/signup | Development | Praneeth | 4 | 3.5 | Done
Client meeting | Coordination | Praneeth, Vivek | 1.5 | 0.75 | Done |  | 0.75 | 100
Client meeting - MOM | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 0.5 | Done |  | 0.5 | 100
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 8
Admin Dashboard | Development | Praneeth | 4 | 3 | Done |  | 1 | 33.3333
Advertiser Dashboard | Development | Kriti, Vivek | 3 | 2 | Done |  | 1 | 50
Logistics Partner Dashboard | Development | Sudhan, Karthikeya | 3 | 2 | Done |  | 1 | 50
Backend for form in both admin and customers pages | Development | Sudhan, Karthikeya | 5 | 4 | Done
Admin approval of the ads page | Development | Kriti, Vivek | 5 | 4 | Done
UML for design document | Design | Kriti | 2 | 1.5 | Done
Team Meeting | Coordination | All | 1 | 0.75 | Done | Discussed all the points that are needed to be addressed before client meet | 0.25 | 33.3333
Design rationale | Documentation | Vivek | 2 | 1 | Done
Client meeting | Coordination | All | 1.5 | 0.5 | Done | Planned on Saturday that is March 9th, but got delayed to Tuesday that is March 12th | 1 | 200
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 9
Last week Client meeting - MOM | Documentation | Vivek, Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Sequence Diagram | Design | Sudhan, Karthikeya | 3 | 2 | Done
Design Rationale updated | Documentation | Praneeth | 2 | 1.5 | Done
Design doc | Documentation | All | 5 | 4 | Done
Settings page | Development | Sudhan, Karthikeya | 3 | 3 | Done |  | 0 | 0
External Home page | Development | Vivek, Kriti | 3 | 2 | Done
About page | Development | Vivek, Kriti | 3 | 2 | Done
Mapping customers to ads | Development | Sudhan, Karthikeya | 4 | 3 | Done
Admin Dashboard | Development | Praneeth | 4 | 3 | Done |  | 1 | 33.3333
Advertiser Dashboard | Development | Kriti, Vivek | 4 | 3 | Done |  | 1 | 33.3333
Logistics Partner Dashboard | Development | Sudhan, Karthikeya | 4 | 3 | Done |  | 1 | 33.3333
Team Meeting | Coordination | All | 1 | 1 | Done | Discussed all the points that are needed to be addressed before client meet | 0 | 0
Client meeting | Coordination | Praneeth | 1 | 0.5 | Done |  | 0.5 | 100
Client meeting - MOM | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 10
R1 Presentation | Documentation | Praneeth, Vivek | 4 | 3 | Done |  | 1 | 33.3333
Demo Video | Documentation | Sudhan, Karthikeya | 2 | 1 | Done
Update design doc | Documentation | Kriti | 2 | 1 | Done
Update Test plan | Documentation | Praneeth, Vivek | 2 | 1.5 | Done
Testing the website fro R1 requirements | Testing | All | 4 | 3 | Done |  | 1 | 33.3333
Team Meeting | Coordination | Sudhan | 1 | 0.5 | Done |  | 0.5 | 100
Client meeting | Coordination | Praneeth, Vivek | 1 | 0.5 | Done |  | 0.5 | 100
Client meeting - MOM | Documentation | Karthikeya | 1 | 0.5 | Done |  | 0.5 | 100
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 11
Distribute R2 work | Coordination | All | 1 | 1 | Done |  | 0 | 0
Search more interaction systems | Requirements | All | 2 | 1.5 | Done |  | 0.5 | 33.3333
Start ML algorithm | Development | Praneeth | 4 | 3 | Done
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 1 | Done |  | 0 | 0
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 12
Start QR tracking | Requirements | Sudhan, Karthikeya | 5 | 5 | Done |  | 0 | 0
Start mapping algorithm | Development | Praneeth | 5 | 4 | Done
Start payment gateway | Requirements | Kriti, Vivek | 5 | 6 | Done |  | -1 | 16.6667
Design Logo | Design | Vivek | 4 | 3 | Done |  | 1 | 33.3333
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 1 | Done | Granulated tasks for Release-2 | 0 | 0
Client meeting | Coordination | Praneeth, Vivek | 1 |  | Done | Postponed due to quizzes
Client meeting - MOM | Documentation | Kriti, Vivek | 1 |  | Done | Will be updated after client meet
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 13
Payment Gateway boilterplate Test | Development | Kriti, Vivek | 7 | 4 | Done |  | 3 | 75
QR link generation, pages | Development | Sudhan, Karthikeya | 8 | 4 | Done |  | 4 | 100
Mapping algorithm | Development | Praneeth | 7 | 4 | Done |  | 3 | 75
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 1 | Done |  | 0 | 0
Client meeting - MOM | Documentation | Kriti, Vivek | 1 | 0.5 | Done | Scheduled on April 6th but got delayed to April 8th and has been done | 0.5 | 100
Client meeting | Coordination | Praneeth, Vivek | 1 | 0.65 | Done | Scheduled on April 6th but got delayed to April 8th and has been done | 0.35 | 53.8462
Status tracker | Documentation | Praneeth, Vivek | 1 | 0.5 | Done |  | 0.5 | 100
Week 14
Payment Gateway boilterplate Test | Development | Kriti, Vivek | 7 | 6 | Done |  | 1 | 16.6667
QR link generation, pages | Development | Sudhan, Karthikeya | 8 | 7 | Done |  | 1 | 14.2857
Mapping algorithm | Development | Praneeth | 7 | 6 | Done |  | 1 | 16.6667
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 1 | Done |  | 0 | 0
Client meeting - MOM | Documentation | Kriti, Vivek | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client meeting | Coordination | Praneeth, Vivek | 1 | 0.5 | Done |  | 0.5 | 100
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 15
Payment pages without integration of the gateway | Development | Kriti, Vivek | 5 | 4 | Done |  | 1 | 25
The containers left in the admin dashboard | Development | Kriti, Vivek | 5 | 4 | Done
QR link generation, pages | Development | Sudhan, Karthikeya | 8 | 7 | Done |  | 1 | 14.2857
Mapping algorithm | Development | Praneeth | 7 | 7 | Done |  | 0 | 0
Updating all the documents | Documentation | All | 3 | 3 | Done | Since the payment gateway integration was cancelled
Team Meeting | Coordination | Sudhan, Karthikeya | 1 | 1 | Done |  | 0 | 0
Database population fro R2 | Development | All | 1.5 | 1 | Done
System testing | Testing | All | 3 | 3 | Done
Acceptance testing | Testing | All | 3 | 3 | Done
R2 presentation | Documentation | All | 3 | 2 | Done
Client meeting - MOM | Documentation | Kriti, Vivek | 1 | 0.75 | Done |  | 0.25 | 33.3333
Client meeting | Coordination | Praneeth, Vivek | 1 | 0.5 | Done |  | 0.5 | 100
Status tracker | Documentation | Kriti | 1 | 0.5 | Done |  | 0.5 | 100
Week 16
Note on C5: SE: The person responsible for ensuring completion, not necessarily all the people doing it
Note on G5: swami: Insert your own comments
Note on H5: SE: This field is updated automatically